## Sheet1
Week | Section 1 | Section 2 |  |  | Section 3 |  | Section 4
|  | Done | Learned | Problems | Goal | Responsible for
1 |  | 1. Team Discussion about Roles and responsibilities and choice of app to be developed 2. Created a team name and logo 3. Brainstormed for Requirement Gathering 4. Blog and Team Presentation 5. Received requirements for building Basic prototype | 1. Team Work - one cannot possess every required skill 2. SCRUM Model 3. Effective communication skills | 1. Channel of communication Initially used WhatsApp group chat, was not effective. To overcome this problem, we started using Trello - task management tool | 1. Software Design 2. User stories and Use case diagram 3. Activity design 4. Blog Writing | 1. Harish 2. Abhivanth 3. Logesh 4. Shudharsan | 1. Build a basic prototype 2. Create User stories and Use Case diagrams 3. Update Blog and presentation